PLP Cohort 1 — Operations Manual

Your week-by-week field guide for running Pure Leadership Power™ Certification Cohort 1 manually before the delivery platform is fully built.

Cohort 1 at a glance

Dates · June 15 — July 27, 2026 (6 weeks + capstone week) Live calls · Tuesdays 12:00–1:30pm ET Capstone week · July 21 (review) → July 25 (defenses) → July 27 (graduation) Cohort size · 24 leaders max · 12 minimum to launch Price · $1,997 Certification · $497 Library · $4,997 Founders' Circle Walter time · ~6 hrs/week (live call + reviews)

Pre-cohort timeline

Today (May 8) → June 15 launch = ~5 weeks. Sequence:

Week 1 (May 8–14) · Open applications, send to email list + LinkedIn

Week 2 (May 15–21) · Review apps, accept first 16, waitlist 8

Week 3 (May 22–28) · Send accepted leaders welcome email + intake survey

Week 4 (May 29–Jun 4) · Issue PLP cohort licenses, peer-pod matchmaking

Week 5 (Jun 5–11) · Final logistics, calendar invites, kickoff prep

Mon Jun 15 · Cohort launch

Acceptance decision rubric

Accept the leader if 3 of 4 conditions hold. Otherwise waitlist (default) or pass.

| Signal | Strong (auto-accept) | Weak (waitlist) |
| --- | --- | --- |
| Why now (essay quality) | Specific growth edge named. Real stake. >150 words. | Vague generalities. <100 words. |
| Role + team size | Director+ leading 10–500. | IC or leading <5 (waitlist) or >1,000 (Founders' tier). |
| Healthcare context | Acute care, ambulatory, payer, public-health leadership | Outside healthcare entirely (pass unless exceptional) |
| Tier selected | Cohort or Founders' | Library only (separate path — auto-issue Library license) |

License issuance

When you accept a Cohort applicant, issue their PLP cohort license via the Control Tower:

Open https://wd-tower-4a5a6a.pages.dev → click 👑 Issue a license tile

Email = applicant's email · Tier = member · Days = 200 (covers 6 cohort weeks + 6 mo Member access)

Check 'Email the welcome message to them now'

Submit. License token will display — copy to peer-pod sheet for backup

NOTE ON FOUNDERS' CIRCLE

Same flow but tier = pro and days = 365. Then schedule the 3 × 60-min 1:1s in your calendar manually. Founders' get their own Slack-DM channel with you (use whatever messaging you prefer).

Live cohort call playbook (90 min)

00:00 – 00:08 · Walter opens · what's new since last week · pulse check 00:08 – 00:30 · Concept teach (this week's attribute) 00:30 – 01:00 · Live drill · 2 prepared scenarios + 1 from cohort 01:00 – 01:20 · Scorecard review · 3 volunteer cohort members share their week 01:20 – 01:30 · Pod assignments · this week's homework · close

TOOLS USED

Zoom (or Riverside if you want recordings to be premium)

Mural or shared Google Doc for the live drill

Coaching Twin (open in browser tab) for the scorecard review

Weekly structure for cohort members

Repeat for weeks 2–5 (Confident Humility, Reasoned Reverence, Fierce Resolve, Genuine Partnership):

| Mon AM | 4 short video lessons drop in Drive folder (10–12 min each) |
| --- | --- |
| Tue 12pm ET | Live cohort call (90 min) |
| Wed–Thu | Apply the attribute to a real meeting · paste transcript into Coaching Twin |
| Fri | Submit weekly scorecard summary in shared sheet (just composite + this week's attribute score) |
| Sat 11am ET (optional) | 30-min peer pod call |
| Sun | Rest. Make Tuesday's standup something to look forward to. |

Capstone week (Jun 21–27)

MON — SUBMISSION OPENS

Cohort members submit a final meeting transcript via the Coaching Twin → Download → email PDF to walter@thedutchmentor.com with subject: 'PLP Capstone · [Name]'.

WED–THU — DEFENSES

Schedule 24 × 15-min capstone defenses across two days. Use Calendly with a 6-hour daily limit. Each defense:

· 5 min: cohort member walks through their scorecard journey + biggest delta + biggest miss

· 5 min: Walter + a pre-assigned peer reviewer ask one question each

· 5 min: Walter pronounces 'certified' or 'not yet' with one specific behavior to address

FRI — GRADUATION CALL

60-min cohort-wide graduation. Each leader gets 60 sec to share their 'one thing'. You issue Pure Leadership Power™ Cohort 1 badges (LinkedIn-shareable URL + image asset). Toast the cohort.

What you ship at graduation (per leader)

Personalized PDF certificate (template below)

LinkedIn-shareable badge image (hosted on plpcert.pages.dev/badge/{license-id}.png)

6-month Coaching Twin Member access (auto-extends from license)

Cohort 1 alumni private channel (Slack or Circle) — community for life

Quarterly check-in scorecard (90, 180, 270 days post-grad)

Risk register · what could break

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Under-enrollment (<12) | Medium | Open Cohort 1 to your warm list at $1,497 (Founder's discount). Don't run with <8. |
| Walter calendar drift | High | Block Tuesdays 11:30–2:00pm ET as recurring focus block May 8–Aug 1. |
| Capstone burnout | Medium | Spread defenses Wed/Thu. Take Friday morning off. The graduation call is your reward. |
| Tech failure on live call | Low | Riverside as primary, Zoom as fallback. Have phone-dial-in numbers ready. |