PLP Cohort 1 — Master Operations README

What's in this folder. Read this first.

Files in this folder

Cohort1_Operations_Manual.docx

Master playbook — pre-cohort timeline, acceptance rubric, license issuance, weekly call playbook, capstone week, risk register.

Welcome_Email_Templates.docx

Acceptance email (cohort + library variants). Send within 24h of accepting.

Live_Call_Setup_Guide.docx

Zoom + Riverside + Calendly setup. One-time setup on May 25–28.

Pre_Cohort_Intake_Survey.docx

13-question survey to send accepted cohort members 2 weeks before kickoff.

Drive_Folder_Structure.docx

Google Drive folder spec — recreate for cohort to access.

Peer_Pod_Matchmaking.xlsx

Cohort tracker · pod-matching algorithm · 6-week schedule · pre-seeded with 3 sample rows.

Capstone_Rubric.pdf

2-page printable rubric — page 1 scoring + decision matrix · page 2 peer-reviewer guide.

Cohort 1 critical path

Use this as your week-by-week checklist:

| Window | Walter does | Sonny / Ops does |
| --- | --- | --- |
| May 8–14 | Open applications · drive traffic to plpcert.pages.dev | Sonny v2 LinkedIn outreach starts |
| May 15–21 | Read every application · accept first 16 · waitlist 8 | Send accept emails (Welcome_Email_Templates) |
| May 22–28 | Set up Zoom + Calendly + Drive folder · record Welcome video | Send intake survey to all accepted |
| May 25–Jun 12 | Record Week 1 + Week 2 lessons (8 videos · 80 min) | Issue PLP cohort licenses via Control Tower |
| Jun 5–11 | Match pods (Peer_Pod_Matchmaking.xlsx) | Send calendar invites · post pod assignments |
| Jun 13 | Review baseline scorecards as they come in | Send Day-Before email |
| Jun 16 | RUN COHORT KICKOFF · Tuesday 12pm ET | Watch chat · take attendance · post replay by Wed |
| Jun 17–Jul 21 | Run Tuesday calls · review pod check-ins each Friday | Each Sunday: populate next week's Drive folder |

Cross-references

Public sales page: https://plpcert.pages.dev

Application admin view: https://dutch-mentor.thedutchmentor.workers.dev/plp-applications?key=ADMIN_KEY

Coaching Twin (cohort tool): https://coachingtwin.pages.dev

Issue licenses: https://wd-tower-4a5a6a.pages.dev → 👑 Issue a license tile

Curriculum delivery (when built): https://plpcert.pages.dev/curriculum

Operating principle for Cohort 1

Cohort 1 is the recording cohort. Don't pretend the platform is finished. Tell cohort members you're recording lessons in parallel, and they're getting the live call PLUS the recordings of their own cohort. They're getting Cohort 0 Founders' status — even at the Cohort 1 price.

If you ship Cohort 1 with 14 leaders who graduate proud and visible, Cohort 2 sells itself.